## jtrac
ID | Summary | Status | Logged By | Assigned To | Priority | Time Stamp
PUNEGEP-1 | write javadoc | Fixed | Admin |  | Highest | 2007-12-30 02:00
PUNEGEP-8 | optimize. Think about CPU and memory usage. profile it and remove the bottlenecks. | Open | Admin | Admin | Highest | 2007-12-30 02:19
PUNEGEP-12 | figure out how 'rates' are used in mutation, transposition and recombination | Fixed | Admin |  | Highest | 2007-12-30 02:20
PUNEGEP-13 | check out how fitness function works and how you can tackle it | Fixed | Admin |  | Highest | 2007-12-30 03:24
PUNEGEP-21 | think how to deal with constants and parameters | Open | Admin | Admin | Highest | 2008-01-11 00:32
PUNEGEP-24 | write a document explaining philosophy, framework approach, salient features, use cases, available grammars, how to extend etc. | Open | Admin | Admin | Highest | 2008-02-04 00:44
PUNEGEP-25 | change project name to amiba and make all the related changes | Fixed | Admin |  | Highest | 2008-02-04 01:10
PUNEGEP-26 | provide a method on the Individual which lets evaluate a bunch of test data and returns corresponding values according to the Individual | Fixed | Admin |  | Highest | 2008-02-04 02:42
PUNEGEP-27 | write impl for graph grammar | Open | Admin | Admin | Highest | 2008-02-08 01:41
PUNEGEP-2 | apply checkstyle and pmd | Open | Admin | Admin | High | 2007-12-30 02:16
PUNEGEP-3 | write test cases | Open | Admin | Admin | High | 2007-12-30 02:16
PUNEGEP-5 | think how generics or abstarct factory pattern might improve the code | Fixed | Admin |  | High | 2007-12-30 02:17
PUNEGEP-6 | apply schema validation for PuneGEPConfig.xml | Open | Admin | Admin | High | 2007-12-30 02:18
PUNEGEP-9 | rationalize packages | Fixed | Admin |  | High | 2007-12-30 02:19
PUNEGEP-10 | evaluate the access rights structure | Open | Admin | Admin | High | 2007-12-30 02:19
PUNEGEP-20 | decide a logo and a line for PuneGEP | Open | Admin | Admin | High | 2008-01-09 02:49
PUNEGEP-4 | consider whether Character class should be used to represent symbols or it should be String | Open | Admin | Admin | Medium | 2007-12-30 02:17
PUNEGEP-11 | add multiple end conditions | Open | Admin | Admin | Medium | 2007-12-30 02:20
PUNEGEP-14 | decide about the reseeding of RandomData so that multiple instances give different values | Open | Admin | Admin | Medium | 2007-12-30 04:21
PUNEGEP-16 | think what part of mutation, transposition and recombination processing should go in Individual | Open | Admin | Admin | Medium | 2008-01-04 23:05
PUNEGEP-17 | think if genes should be treated as the indivisible units for recombination | Fixed | Admin |  | Medium | 2008-01-08 01:32
PUNEGEP-19 | think how to integrate the use of fitness cases into the framework | Fixed | Admin |  | Medium | 2008-01-09 02:48
PUNEGEP-23 | think if the replacement for infeasible Individuals should be from the population or a new feasible Individual | Open | Admin | Admin | Medium | 2008-02-03 23:23
PUNEGEP-7 | should PuneGEPConfig.xml processing be moved to XSLT? | Fixed | Admin |  | Low | 2007-12-30 02:18
PUNEGEP-15 | Think about cut&paste vs copy&paste transposition, as well as other transposition related issues. | Open | Admin | Admin | Low | 2008-01-04 01:38
PUNEGEP-18 | think if we need to move to long and double from current int and float | Fixed | Admin |  | Low | 2008-01-09 01:59
PUNEGEP-22 | think if we need to move from int to long | Open | Admin | Admin | Low | 2008-01-23 02:40